## R1
Task # | Iteration | Module Name | RCT.ID | Core Feature | Task Description | Start Date | End Date | Status | Task Owner
1 | R1-I1 | 02.Account profile management | 2.01 | Account Info | Implement core functionality according to the specified requirements | 2021-02-10 | 2021-02-20 | 100% | Midhuna
2 | R1-I1 | 02.Account profile management | 2.01 | Account Info | Implement GUI requirements according to the specified requirements | 2021-02-10 | 2021-02-22 | 100% | Midhuna
3 | R1-I1 | 02.Account profile management | 2.01 | Account Info | Implement DF-In - Data Flow In - to ensure that the subscribed customer details are displayed correctly from the Sign Up page | 2021-02-10 | 2021-02-22 | 100% | Midhuna
4 | R1-I1 | 02.Account profile management | 2.01 | Account Info | Implement ET - Entitlements - to ensure that only subscriber customer is able to access Account Info page | 2021-02-10 | 2021-02-24 | 100% | Midhuna
5 | R1-I1 | 02.Account profile management | 2.01 | Account Info | Implement CN - Connectivity - to ensure that the page is available only when there is internet connectivity so the page displays up to date infromation | 2021-02-10 | 2021-02-24 | 100% | Midhuna
6 | R1-I1 | 02.Account profile management | 2.01 | Account Info | Implement FV - Field Validation - on field to ensure accurate modifications: "First Name" should meet the validatoin criteria, field is required and not null/blank | 2021-02-10 | 2021-02-26 | 100% | Midhuna
7 | R1-I1 | 02.Account profile management | 2.01 | Account Info | Implement FV - Field Validation - on field to ensure accurate modifications: "Last Name" should meet the validatoin criteria, field is required and not null/blank | 2021-02-10 | 2021-02-26 | 100% | Midhuna
8 | R1-I1 | 02.Account profile management | 2.01 | Account Info | Implement FV - Field Validation - on field to ensure accurate modifications: "Username" should meet the validatoin criteria, field is required and not null/blank | 2021-02-10 | 2021-02-26 | 100% | Midhuna
9 | R1-I1 | 02.Account profile management | 2.01 | Account Info | Implement the pen icons to ensure that subscriber customer can edit/save the updated details | 2021-02-10 | 2021-02-26 | 100% | Midhuna
10 | R1-I1 | 02.Account profile management | 2.01 | Account Info | Implement FV - Field Validation - on field to ensure accurate modifications: "Email Address" should meet the validatoin criteria, field length and character format | 2021-02-10 | 2021-02-26 | 100% | Midhuna
11 | R1-I1 | 02.Account profile management | 2.01 | Account Info | Implement FV - Field Validation - on field to ensure accurate modifications: "Password" should meet the validatoin criteria, field length and character format | 2021-02-10 | 2021-02-26 | 100% | Midhuna
12 | R1-I1 | 02.Account profile management | 2.01 | Account Info | Create test cases for validation | 2021-02-24 | 2021-02-26 | 100% | Akshay/Shubham
13 | R1-I1 | 02.Account profile management | 2.01 | Account Info | Create test cases for functionality | 2021-02-24 | 2021-02-26 | 100% | Akshay/Shubham
14 | R1-I1 | 02.Account profile management | 2.01 | Account Info | Test the feature functionalities | 2021-02-26 | 2021-02-28 | 100% | Tejashri
15 | R1-I1 | 02.Account profile management | 2.01 | Account Info | Document the test execution log | 2021-02-28 | 2021-03-02 | 100% | Irina/Onye
16 | R1-I1 | 02.Account profile management | 2.01 | Account Info | Implement bug fixes | 2021-03-02 | 2021-03-04 | 100% | Midhuna
17 | R1-I1 | 02.Account profile management | 2.01 | Account Info | Retest the feature functionalities after the bugs were fixed to determine if ready for release | 2021-03-04 | 2021-03-05 | 100% | Tejashri
18 | R1-I1 | 04. Checkout | 4.01 | Entry/modify payment info | Implement core functionality according to the specified requirements | 2021-02-10 | 2021-02-20 | 100% | Miduna
19 | R1-I1 | 04. Checkout | 4.01 | Entry/modify payment info | Implement GUI requirements according to the specified requirements | 2021-02-10 | 2021-02-20 | 100% | Miduna
20 | R1-I1 | 04. Checkout | 4.01 | Entry/modify payment info | Implement DF-In - Data Flow Out - the data should feed to the Payment Processing feature | 2021-02-10 | 2021-02-20 | 100% | Miduna
21 | R1-I1 | 04. Checkout | 4.01 | Entry/modify payment info | Implement ET - Entitlements - to ensure that only subscriber customer is able to access Payment Info page | 2021-02-10 | 2021-02-20 | 100% | Miduna
22 | R1-I1 | 04. Checkout | 4.01 | Entry/modify payment info | Implement CN - Connectivity - to ensure that the page is available only when there is internet connectivity so the page displays up to date infromation | 2021-02-10 | 2021-02-20 | 100% | Miduna
23 | R1-I1 | 04. Checkout | 4.01 | Entry/modify payment info | Implement FV - Field Validation - on field to ensure accurate modifications: "Name on the Card" should meet the validatoin criteria, field is required and not null/blank | 2021-02-10 | 2021-02-22 | 100% | Miduna
24 | R1-I1 | 04. Checkout | 4.01 | Entry/modify payment info | Implement FV - Field Validation - on field to ensure accurate modifications: "Street Address" should meet the validatoin criteria, field is required and not null/blank | 2021-02-10 | 2021-02-22 | 100% | Miduna
25 | R1-I1 | 04. Checkout | 4.01 | Entry/modify payment info | Implement FV - Field Validation - on field to ensure accurate modifications: "City" should meet the validatoin criteria, field is required and not null/blank | 2021-02-10 | 2021-02-24 | 100% | Miduna
26 | R1-I1 | 04. Checkout | 4.01 | Entry/modify payment info | Implement FV - Field Validation - on field to ensure accurate modifications: "State" should meet the validatoin criteria, field is required and not null/blank | 2021-02-10 | 2021-02-24 | 100% | Miduna
27 | R1-I1 | 04. Checkout | 4.01 | Entry/modify payment info | Implement FV - Field Validation - on field to ensure accurate modifications: "Zip" should meet the validatoin criteria, field is required and not null/blank | 2021-02-10 | 2021-02-26 | 100% | Miduna
28 | R1-I1 | 04. Checkout | 4.01 | Entry/modify payment info | Implement FV - Field Validation - on field to ensure accurate modifications: "Country" should meet the validatoin criteria, field is required and not null/blank | 2021-02-10 | 2021-02-26 | 100% | Miduna
29 | R1-I1 | 04. Checkout | 4.01 | Entry/modify payment info | Implement the Save button to ensure that subscriber customer can save the updated details | 2021-02-10 | 2021-02-26 | 100% | Miduna
30 | R1-I1 | 04. Checkout | 4.01 | Entry/modify payment info | Implement FV - Field Validation - on field to ensure accurate modifications: "Card Number" should meet the validatoin criteria, field length and character format | 2021-02-10 | 2021-02-26 | 100% | Miduna
31 | R1-I1 | 04. Checkout | 4.01 | Entry/modify payment info | Implement FV - Field Validation - on field to ensure accurate modifications: "Expiration Date" should meet the validatoin criteria, field length and character format | 2021-02-10 | 2021-02-26 | 100% | Miduna
32 | R1-I1 | 04. Checkout | 4.01 | Entry/modify payment info | Implement FV - Field Validation - on field to ensure accurate modifications: "Security Code" should meet the validatoin criteria, field length and character format | 2021-02-10 | 2021-02-26 | 100% | Miduna
33 | R1-I1 | 04. Checkout | 4.01 | Entry/modify payment info | Create test cases for validation | 2021-02-24 | 2021-02-26 | 100% | Akshay/Shubham
34 | R1-I1 | 04. Checkout | 4.01 | Entry/modify payment info | Create test cases for functionality | 2021-02-24 | 2021-02-26 | 100% | Akshay/Shubham
35 | R1-I1 | 04. Checkout | 4.01 | Entry/modify payment info | Test the feature functionalities | 2021-02-26 | 2021-02-28 | 100% | Tejashri
36 | R1-I1 | 04. Checkout | 4.01 | Entry/modify payment info | Document the test execution log | 2021-02-28 | 2021-03-02 | 100% | Irina/Onye
37 | R1-I1 | 04. Checkout | 4.01 | Entry/modify payment info | Implement bug fixes | 2021-03-02 | 2021-03-04 | 100% | Midhuna
38 | R1-I1 | 04. Checkout | 4.01 | Entry/modify payment info | Retest the feature functionalities after the bugs were fixed to determine if ready for release | 2021-03-04 | 2021-03-05 | 100% | Tejashri
Formulas:
Start Date = [End Date]-2
End Date = [Start Date, row below]

## R2
Task # | Iteration | Module Name | RCT.ID | Core Feature | Task Description | Start Date | End Date | Status | Task Owner
1 | R1-I2 | 04. Checkout | 4.02 | Entry/modify delivery adress | Implement core functionality according to the specified requirements | 2021-03-12 | 2021-03-15 | 100% | Midhuna
2 | R1-I2 | 04. Checkout | 4.02 | Entry/modify delivery adress | Implement GUI requirements according to the specified requirements | 2021-03-12 | 2021-03-15 | 100% | Midhuna
3 | R1-I2 | 04. Checkout | 4.02 | Entry/modify delivery adress | Implement ET - Entitlements - to ensure that only subscriber customer is able to access Delivery Info page | 2021-03-12 | 2021-03-15 | 100% | Midhuna
4 | R1-I2 | 04. Checkout | 4.02 | Entry/modify delivery adress | Implement CN - Connectivity - to ensure that the page is available only when there is internet connectivity so the page displays up to date infromation | 2021-03-12 | 2021-03-15 | 100% | Midhuna
5 | R1-I2 | 04. Checkout | 4.02 | Entry/modify delivery adress | Impelement DDV - Data-Dependency Validation - to ensure that delivery address details cannot be deleted if there is a pending order in the system | 2021-03-12 | 2021-03-15 | 100% | Midhuna
6 | R1-I2 | 04. Checkout | 4.02 | Entry/modify delivery adress | Implement DF-In - Data Flow Out - the data should feed to the Payment Processing feature | 2021-03-12 | 2021-03-15 | 100% | Midhuna
7 | R1-I2 | 04. Checkout | 4.02 | Entry/modify delivery adress | Implement the "Use this address" button to ensure that subscriber customer can save the updated details | 2021-03-12 | 2021-03-15 | 100% | Midhuna
8 | R1-I2 | 04. Checkout | 4.02 | Entry/modify delivery adress | Implement FV - Field Validation - on field to ensure accurate modifications: "Name" should meet the validatoin criteria, field is required and not null/blank | 2021-03-12 | 2021-03-15 | 100% | Midhuna
9 | R1-I2 | 04. Checkout | 4.02 | Entry/modify delivery adress | Implement FV - Field Validation - on field to ensure accurate modifications: "Street Address" should meet the validatoin criteria, field is required and not null/blank | 2021-03-12 | 2021-03-15 | 100% | Midhuna
10 | R1-I2 | 04. Checkout | 4.02 | Entry/modify delivery adress | Implement FV - Field Validation - on field to ensure accurate modifications: "City" should meet the validatoin criteria, field is required and not null/blank | 2021-03-12 | 2021-03-15 | 100% | Midhuna
11 | R1-I2 | 04. Checkout | 4.02 | Entry/modify delivery adress | Implement FV - Field Validation - on field to ensure accurate modifications: "State" should meet the validatoin criteria, field is required and not null/blank | 2021-03-12 | 2021-03-15 | 100% | Midhuna
12 | R1-I2 | 04. Checkout | 4.02 | Entry/modify delivery adress | Implement FV - Field Validation - on field to ensure accurate modifications: "Zip" should meet the validatoin criteria, field is required and not null/blank | 2021-03-12 | 2021-03-15 | 100% | Midhuna
13 | R1-I2 | 04. Checkout | 4.02 | Entry/modify delivery adress | Implement FV - Field Validation - on field to ensure accurate modifications: "Country" should meet the validatoin criteria, field is required and not null/blank | 2021-03-12 | 2021-03-15 | 100% | Midhuna
14 | R1-I2 | 04. Checkout | 4.02 | Entry/modify delivery adress | Create test cases for validation | 2021-03-15 | 2021-03-16 | 100% | Akshay/Shubham
15 | R1-I2 | 04. Checkout | 4.02 | Entry/modify delivery adress | Create test cases for functionality | 2021-03-15 | 2021-03-16 | 100% | Akshay/Shubham
16 | R1-I2 | 04. Checkout | 4.02 | Entry/modify delivery adress | Test the feature functionalities | 2021-03-16 | 2021-03-17 | 100% | Tejashri
17 | R1-I2 | 04. Checkout | 4.02 | Entry/modify delivery adress | Document the test execution log | 2021-03-16 | 2021-03-17 | 100% | Irina/Onye
18 | R1-I2 | 04. Checkout | 4.02 | Entry/modify delivery adress | Implement bug fixes | 2021-03-17 | 2021-03-18 | 100% | Midhuna
19 | R1-I2 | 04. Checkout | 4.02 | Entry/modify delivery adress | Retest the feature functionalities after the bugs were fixed | 2021-03-18 | 2021-03-18 | 100% | Tejashri
20 | R1-I2 | 04. Checkout | 4.03 | Order processing | Implement core functionality according to the specified requirements | 2021-03-19 | 2021-03-22 | 100% | Midhuna
21 | R1-I2 | 04. Checkout | 4.03 | Order processing | Implement GUI requirements according to the specified requirements | 2021-03-19 | 2021-03-22 | 100% | Midhuna
22 | R1-I2 | 04. Checkout | 4.03 | Order processing | Implement DF-In - Data Flow In - so that data flows from the “Payment Info” and “Delivery Address” for the order to be processed | 2021-03-19 | 2021-03-22 | 100% | Midhuna
23 | R1-I2 | 04. Checkout | 4.03 | Order processing | Implement ET - Entitlements - to ensure that only subscriber customer is able to access payment processing page | 2021-03-19 | 2021-03-22 | 100% | Midhuna
24 | R1-I2 | 04. Checkout | 4.03 | Order processing | Implement CL - Calculations - to ensure that the total amount to be processed is calculated based on the customer’s subscription plan | 2021-03-19 | 2021-03-22 | 100% | Midhuna
25 | R1-I2 | 04. Checkout | 4.03 | Order processing | Implement CN - Connectivity - to ensure that the page is available only when there is internet connectivity so the page displays up to date infromation | 2021-03-19 | 2021-03-22 | 100% | Midhuna
26 | R1-I2 | 04. Checkout | 4.03 | Order processing | Impelement DDV - Data-Dependency Validation - to ensure that delivery address details and payment details cannot be deleted if there is order being placed | 2021-03-19 | 2021-03-22 | 100% | Midhuna
27 | R1-I2 | 04. Checkout | 4.03 | Order processing | Implement DF-In - Data Flow Out - to ensure order processing feeds the order details data to the “Order Status” page | 2021-03-19 | 2021-03-22 | 100% | Midhuna
28 | R1-I2 | 04. Checkout | 4.03 | Order processing | Create test cases for validation | 2021-03-22 | 2021-03-23 | 100% | Akshay/Shubham
29 | R1-I2 | 04. Checkout | 4.03 | Order processing | Create test cases for functionality | 2021-03-22 | 2021-03-23 | 100% | Akshay/Shubham
30 | R1-I2 | 04. Checkout | 4.03 | Order processing | Test the feature functionalities | 2021-03-23 | 2021-03-24 | 100% | Tejashri
31 | R1-I2 | 04. Checkout | 4.03 | Order processing | Document the test execution log | 2021-03-23 | 2021-03-24 | 100% | Irina/Onye
32 | R1-I2 | 04. Checkout | 4.03 | Order processing | Implement bug fixes | 2021-03-24 | 2021-03-25 | 100% | Midhuna
33 | R1-I2 | 04. Checkout | 4.03 | Order processing | Retest the feature functionalities after the bugs were fixed | 2021-03-25 | 2021-03-25 | 100% | Tejashri
Formulas:
End Date = [Start Date, row below]