## Road Map
Craving! - Road Map
|  |  |  | Release 1 |  | Release 2
Application Modules | Feature Backlog |  | Story Points | Iteration 1 - 3/5/21 | Iteration 2 - 3/26/21 | Iteration 3 - 4/9/21 | Iteration 4 - 4/30/21
01. Authentication | 01.01 | Login | 4
| 01.02 | SignUp | 4
| 01.03 | Restore Credentials | 4
02. Account Profile Management | 02.01 | Account Info | 4 | x
| 02.02 | Likes/Dislikes | 8
03. Subscription Management | 03.01 | Select/Pause Plan | 6
| 03.02 | Skip future order | 8
| 03.03 | Remove/add products in box | 6
| 03.04 | Order cancel/history | 5 |  |  |  | x
04. Checkout | 04.01 | Entry/modify payment info | 5 | x
| 04.02 | Entry/modify delivery address | 3 |  | x
| 04.03 | Order processing | 7 |  | x
05. Support | 05.01 | Ticket submission | 4 |  |  | x
| 05.02 | Ticket history/resolution | 5 |  |  | x
06. Product Review | 06.01 | Leave review | 6 |  |  |  | x
| 06.02 | Product rating | 6
| 06.03 | Add/display favorites | 6
| 06.04 | Share on social media | 8
07. Internal Management | 07.01 | Enter/Modify ad ifno | 3
| 07.02 | Report Generation | 8
| 07.03 | Sponsored Posts | 6
| 07.04 | Enter/Modify/Display Product info | 3
| 07.05 | Order Status | 3
| 07.06 | Tracking numbers | 4
| 07.07 | Manage subscription plan | 3
|  | Velocity : |  | 9 | 10 | 9 | 11
Spring 2021 R2
Spring 2021 R1
Fall 2020
If time permits Spring 2021

## Story Map (hidden)
Craving! - User Story Map
EPICs |  | EPIC 1 - Account Profile Mgt |  | EPIC 2 - Subscription Mgt |  | EPIC 3 - Checkout |  | EPIC 4 - Support |  | EPIC 5 - Product Review
EPIC 1 - Account Profile Management | User Stories | 02.01 | Account Info |  |  | 04.01 | Entry/modify payment info |  |  |  |  | Iteration 1
EPIC 2 - Subscription Management | [5 empty] | 04.02 | Entry/modify delivery address
EPIC 3 - Checkout | [5 empty] | 04.03 | Order processing |  |  |  |  | Iteration 2
EPIC 4 - Support | [7 empty] | 05.01 | Ticket submission
EPIC 5 - Product Review | [7 empty] | 05.02 | Ticket history/resolution |  |  | Iteration 3
|  |  |  | 03.04 | Order cancel/history |  |  |  |  | 06.01 | Leave review | Iteration 4