## I3
Task # | Iteration | Module Name | RCT.ID | Core Feature | Task Description | Start Date | End Date | Status | Task Owner
1 | R2-I3 | 05. Support | 05.01 | Ticket submission | Implement core functionality according to the specified requirements | 2021-03-26 | 2021-04-02 | 100% | Midhuna
2 | R2-I3 | 05. Support | 05.01 | Ticket submission | Implement GUI requirements according to the specified requirements | 2021-03-26 | 2021-04-02 | 100% | Midhuna
3 | R2-I3 | 05. Support | 05.01 | Ticket submission | Implement ET - Entitlements - to ensure that only subscriber customer is able to Ticket Submission page | 2021-03-26 | 2021-04-02 | 100% | Midhuna
4 | R2-I3 | 05. Support | 05.01 | Ticket submission | Implement CN - Connectivity - to ensure that the page is available only when there is internet connectivity so the page displays up to date infromation | 2021-03-26 | 2021-04-02 | 100% | Midhuna
5 | R2-I3 | 05. Support | 05.01 | Ticket submission | Implement DDD - Data Driven Defaults - on field to ensure accurate modifications: "Name" should meet the validatoin criteria | 2021-03-26 | 2021-04-02 | 100% | Midhuna
6 | R2-I3 | 05. Support | 05.01 | Ticket submission | Implement DDD - Data Driven Defaults - on field to ensure accurate modifications: "Email" should meet the validatoin criteria | 2021-03-26 | 2021-04-02 | 100% | Midhuna
7 | R2-I3 | 05. Support | 05.01 | Ticket submission | Implement FV - Field Validation - on field to ensure accurate modifications: "Comment" should meet the validatoin criteria, field is required and not null/blank | 2021-03-26 | 2021-04-02 | 100% | Midhuna
8 | R2-I3 | 05. Support | 05.01 | Ticket submission | Implement the DF-In - Data flow In - the data should feed from account info page | 2021-03-26 | 2021-04-02 | 100% | Midhuna
9 | R2-I3 | 05. Support | 05.01 | Ticket submission | Implement the DF-Out - Data flow Out - the data should flow to Ticket history/resolution page | 2021-03-26 | 2021-04-02 | 100% | Midhuna
10 | R2-I3 | 05. Support | 05.01 | Ticket submission | Implement Submit button | 2021-03-26 | 2021-04-02 | 100% | Midhuna
11 | R2-I3 | 05. Support | 05.01 | Ticket submission | Create test cases for validation | 2021-04-02 | 2021-04-03 | 100% | Shubham
12 | R2-I3 | 05. Support | 05.01 | Ticket submission | Create test cases for functionality | 2021-04-03 | 2021-04-04 | 100% | Shubham
13 | R2-I3 | 05. Support | 05.01 | Ticket submission | Test the feature functionalities | 2021-04-04 | 2021-04-05 | 100% | Onye
14 | R2-I3 | 05. Support | 05.01 | Ticket submission | Document the test execution log | 2021-04-05 | 2021-04-06 | 100% | Tejashri
15 | R2-I3 | 05. Support | 05.01 | Ticket submission | Implement bug fixes | 2021-04-06 | 2021-04-08 | 100% | Midhuna
16 | R2-I3 | 05. Support | 05.01 | Ticket submission | Retest the feature functionalities after the bugs were fixed to determine if ready for release | 2021-04-08 | 2021-04-09 | 100% | Akshay
17 | R2-I3 | 05. Support | 05.02 | Ticket history/resolution | Implement core functionality according to the specified requirements | 2021-03-26 | 2021-04-02 | 100% | Midhuna
18 | R2-I3 | 05. Support | 05.02 | Ticket history/resolution | Implement GUI requirements according to the specified requirements | 2021-03-26 | 2021-04-02 | 100% | Midhuna
19 | R2-I3 | 05. Support | 05.02 | Ticket history/resolution | Implement ET - Entitlements - to ensure that only subscriber customer is able to access Payment Info page | 2021-03-26 | 2021-04-02 | 100% | Midhuna
20 | R2-I3 | 05. Support | 05.02 | Ticket history/resolution | Implement CN - Connectivity - to ensure that the page is available only when there is internet connectivity so the page displays up to date infromation | 2021-03-26 | 2021-04-02 | 100% | Midhuna
21 | R2-I3 | 05. Support | 05.02 | Ticket history/resolution | Implement DF-In - Data Flow In - the data should feed from the Ticket Submission feature | 2021-03-26 | 2021-04-02 | 100% | Midhuna
22 | R2-I3 | 05. Support | 05.02 | Ticket history/resolution | Create test cases for validation | 2021-04-02 | 2021-04-03 | 100% | Shubham
23 | R2-I3 | 05. Support | 05.02 | Ticket history/resolution | Create test cases for functionality | 2021-04-03 | 2021-04-04 | 100% | Shubham
24 | R2-I3 | 05. Support | 05.02 | Ticket history/resolution | Test the feature functionalities | 2021-04-04 | 2021-04-05 | 100% | Onye
25 | R2-I3 | 05. Support | 05.02 | Ticket history/resolution | Document the test execution log | 2021-04-05 | 2021-04-06 | 100% | Tejashri
26 | R2-I3 | 05. Support | 05.02 | Ticket history/resolution | Implement bug fixes | 2021-04-06 | 2021-04-08 | 100% | Midhuna
27 | R2-I3 | 05. Support | 05.02 | Ticket history/resolution | Retest the feature functionalities after the bugs were fixed to determine if ready for release | 2021-04-08 | 2021-04-09 | 100% | Akshay

## I4
Task # | Iteration | Module Name | RCT.ID | Core Feature | Task Description | Start Date | End Date | Status | Task Owner
1 | R2-I4 | 03. Subscription Management | 03.04 | Order cancel/history | Implement core functionality according to the specified requirements | 2021-04-09 | 2021-04-23 | 100% | Midhuna
2 | R2-I4 | 03. Subscription Management | 03.04 | Order cancel/history | Implement GUI requirements according to the specified requirements | 2021-04-09 | 2021-04-23 | 100% | Midhuna
3 | R2-I4 | 03. Subscription Management | 03.04 | Order cancel/history | Implement ET - Entitlements - to ensure that only subscriber customer is able to access Payment Info page | 2021-04-09 | 2021-04-23 | 100% | Midhuna
4 | R2-I4 | 03. Subscription Management | 03.04 | Order cancel/history | Implement CN - Connectivity - to ensure that the page is available only when there is internet connectivity so the page displays up to date infromation | 2021-04-09 | 2021-04-23 | 100% | Midhuna
5 | R2-I4 | 03. Subscription Management | 03.04 | Order cancel/history | Implement DF-In - Data Flow In - the data should feed from the Order Processing feature | 2021-04-09 | 2021-04-23 | 100% | Midhuna
6 | R2-I4 | 03. Subscription Management | 03.04 | Order cancel/history | Create test cases for validation | 2021-04-23 | 2021-04-24 | 100% | Shubham
7 | R2-I4 | 03. Subscription Management | 03.04 | Order cancel/history | Create test cases for functionality | 2021-04-24 | 2021-04-25 | 100% | Shubham
8 | R2-I4 | 03. Subscription Management | 03.04 | Order cancel/history | Test the feature functionalities | 2021-04-25 | 2021-04-26 | 100% | Tejashri
9 | R2-I4 | 03. Subscription Management | 03.04 | Order cancel/history | Document the test execution log | 2021-04-26 | 2021-04-27 | 100% | Tejashri
10 | R2-I4 | 03. Subscription Management | 03.04 | Order cancel/history | Implement bug fixes | 2021-04-27 | 2021-04-29 | 100% | Midhuna
11 | R2-I4 | 03. Subscription Management | 03.04 | Order cancel/history | Retest the feature functionalities after the bugs were fixed to determine if ready for release | 2021-04-29 | 2021-04-30 | 100% | Akshay
12 | R2-I4 | 06. Product Review | 06.01 | Leave review | Implement core functionality according to the specified requirements | 2021-04-09 | 2021-04-23 | 100% | Midhuna
13 | R2-I4 | 06. Product Review | 06.01 | Leave review | Implement GUI requirements according to the specified requirements | 2021-04-09 | 2021-04-23 | 100% | Midhuna
14 | R2-I4 | 06. Product Review | 06.01 | Leave review | Implement ET - Entitlements - to ensure that only subscriber customer is able to Ticket Submission page | 2021-04-09 | 2021-04-23 | 100% | Midhuna
15 | R2-I4 | 06. Product Review | 06.01 | Leave review | Implement CN - Connectivity - to ensure that the page is available only when there is internet connectivity so the page displays up to date infromation | 2021-04-09 | 2021-04-23 | 100% | Midhuna
16 | R2-I4 | 06. Product Review | 06.01 | Leave review | Implement DDD - Data Driven Defaults - to ensure "Name" meets the validatoin criteria | 2021-04-09 | 2021-04-23 | 100% | Midhuna
17 | R2-I4 | 06. Product Review | 06.01 | Leave review | Implement FV - Field Validation - on field to ensure accurate modifications: "Review" should meet the validatoin criteria, field is required and not null/blank | 2021-04-09 | 2021-04-23 | 100% | Midhuna
18 | R2-I4 | 06. Product Review | 06.01 | Leave review | Implement Submit button | 2021-04-09 | 2021-04-23 | 100% | Midhuna
19 | R2-I4 | 06. Product Review | 06.01 | Leave review | Create test cases for validation | 2021-04-23 | 2021-04-24 | 100% | Shubham
20 | R2-I4 | 06. Product Review | 06.01 | Leave review | Create test cases for functionality | 2021-04-24 | 2021-04-25 | 100% | Shubham
21 | R2-I4 | 06. Product Review | 06.01 | Leave review | Test the feature functionalities | 2021-04-25 | 2021-04-26 | 100% | Onye
22 | R2-I4 | 06. Product Review | 06.01 | Leave review | Document the test execution log | 2021-04-26 | 2021-04-27 | 100% | Tejashri
23 | R2-I4 | 06. Product Review | 06.01 | Leave review | Implement bug fixes | 2021-04-27 | 2021-04-29 | 100% | Midhuna
24 | R2-I4 | 06. Product Review | 06.01 | Leave review | Retest the feature functionalities after the bugs were fixed to determine if ready for release | 2021-04-29 | 2021-04-30 | 100% | Akshay