## Team_4_Project_Plan_Craving
Collor Coding | Completed | [5 empty] | Craving!
| In Progress | [5 empty] | Fall 2020
| Not started |  |  |  |  | Week # | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
[6 empty] | Date | 2020-08-25 | 2020-09-01 | 2020-09-08 | 2020-09-15 | 2020-09-22 | 2020-09-29 | 2020-10-06 | 2020-10-13 | 2020-10-20 | 2020-10-27 | 2020-11-03 | 2020-11-10 | 2020-11-17 | 2020-11-24
Project Phase | Activity |  | Task Owner Name | Start Date | End Date | Progress %
Project Initiation | Discuss project proposals |  | Team | 2020-08-25 | 2020-08-25 | 100%
| Confirm Project Team Roles |  | Team | 2020-08-25 | 2020-08-25 | 100%
| Develop two business cases |  | Team | 2020-08-25 | 2020-09-01 | 100%
| Develop Project Initiation Document (PID) |  | Irina Sachovska | 2020-09-01 | 2020-09-08 | 100%
| RACI |  | Irina Sachovska | 2020-09-08 | 2020-09-15 | 100%
| Produce Initial Project Plan |  | Irina Sachovska | 2020-09-08 | 2020-09-15 | 100%
MILESTONE 1: INITIAL PROJECT PLAN COMPLETED
Requirements Definition | Produce BRM diagram, define User Roles |  | Shubham Trivedi | 2020-09-15 | 2020-09-22 | 100%
| Produce Context Diagram |  | Onyekachi Ohiaeri | 2020-09-15 | 2020-09-22 | 100%
| Define System Interfaces |  | Onyekachi Ohiaeri | 2020-09-15 | 2020-09-22 | 100%
| System Requirements Types |  | Onyekachi Ohiaeri | 2020-09-15 | 2020-09-22 | 100%
| Update Project Plan with additional requirement tasks |  | Irina Sachovska | 2020-09-15 | 2020-09-22 | 100%
| Define Business Requirements / BRD |  | Shubham Trivedi | 2020-09-22 | 2020-09-29 | 100%
| Define Functional Decomposition |  | Onyekachi Ohiaeri | 2020-09-22 | 2020-09-29 | 100%
| Produce RCT document |  | Onyekachi Ohiaeri | 2020-09-22 | 2020-09-29 | 100%
| Supplementary requirements (Crosscutting concerns) |  | Onyekachi Ohiaeri | 2020-09-22 | 2020-09-29 | 100%
| Update Project Plan with additional requirement tasks |  | Irina Sachovska | 2020-09-22 | 2020-09-29 | 100%
| Decide which features from RCT to implement this semester |  | Irina Sachovska, Shubham Trivedi | 2020-09-29 | 2020-10-06 | 100%
| Produce analysis diagrams | Use-Case Diagram (UML) | Onyekachi Ohiaeri | 2020-09-29 | 2020-10-06 | 100%
|  | Activity Diagram (UML) | Onyekachi Ohiaeri | 2020-09-29 | 2020-10-06 | 100%
|  | Data-Flow Diagram (Logical) | Onyekachi Ohiaeri | 2020-09-29 | 2020-10-06 | 100%
| Define functional requirements (User Stories) |  | Onyekachi Ohiaeri | 2020-09-29 | 2020-10-06 | 100%
| Update Project Plan with additional requirement tasks |  | Irina Sachovska | 2020-09-29 | 2020-10-06 | 100%
MILESTONE 2: REQUIREMENTS COMPLETED
| ER Diagram (Conceptual) |  | Tejashri Parurkar | 2020-10-06 | 2020-10-20 | 100%
| ER Diagram (Logical) |  | Tejashri Parurkar | 2020-10-06 | 2020-10-20 | 100%
| Database Table Specs (Data Dictionary) |  | Tejashri Parurkar | 2020-10-06 | 2020-10-20 | 100%
| Data-Flow Diagram (Physical) |  | Onyekachi Ohiaeri | 2020-10-06 | 2020-10-20 | 100%
| Update Project Plan with additional requirement tasks |  | Irina Sachovska | 2020-10-06 | 2020-10-20 | 100%
| Architecture design (2 diagrams) (Logical, Process Views) |  | Midhuna Manchi, Tejashri Parurkar | 2020-10-20 | 2020-10-27 | 100%
| Establish GitHub projects |  | Midhuna Manchi, Tejashri Parurkar | 2020-10-20 | 2020-10-27 | 100%
MILESTONE 3: DESIGN COMPLETED
Code | Update Project Plan with additional requirement tasks |  | Irina Sachovska | 2020-10-27 | 2020-11-03 | 100%
| Class Diagram (UML) |  | Midhuna Manchi | 2020-10-27 | 2020-11-03 | 100%
| Sequence Diagram (UML) |  | Midhuna Manchi | 2020-10-27 | 2020-11-03 | 100%
| Source code sample, executable code ready for testing: |  | Midhuna Manchi | 2020-10-27 | 2020-11-10 | 100%
| 01.01 Login | Core Functionality | Midhuna Manchi | 2020-11-03 | 2020-11-10 | 100%
|  | GUI Features | Midhuna Manchi | 2020-11-03 | 2020-11-10 | 100%
|  | Data-Dependency Validation | Midhuna Manchi | 2020-11-03 | 2020-11-10 | 100%
|  | Connectivity | Midhuna Manchi | 2020-11-03 | 2020-11-10 | 100%
|  | Data Flow Out | Midhuna Manchi | 2020-11-03 | 2020-11-10 | 100%
|  | Exception Handling | Midhuna Manchi | 2020-11-03 | 2020-11-10 | 100%
| 01.02 SignUp | Core Functionality | Midhuna Manchi | 2020-11-03 | 2020-11-10 | 100%
|  | GUI Features | Midhuna Manchi | 2020-11-03 | 2020-11-10 | 100%
|  | Connectivity | Midhuna Manchi | 2020-11-03 | 2020-11-10 | 100%
|  | Data Flow Out | Midhuna Manchi | 2020-11-03 | 2020-11-10 | 100%
| 01.03 Restore Credentials | Core Functionality | Midhuna Manchi | 2020-11-03 | 2020-11-10 | 100%
|  | GUI Features | Midhuna Manchi | 2020-11-03 | 2020-11-10 | 100%
|  | Entitlements | Midhuna Manchi | 2020-11-03 | 2020-11-10 | 100%
|  | Field Validation | Midhuna Manchi | 2020-11-03 | 2020-11-10 | 100%
|  | Connectivity | Midhuna Manchi | 2020-11-03 | 2020-11-10 | 100%
|  | Data Flow Out | Midhuna Manchi | 2020-11-03 | 2020-11-10 | 100%
| 03.01 Select/Pause Plan | Core Functionality(Select/Pause) | Midhuna Manchi | 2020-11-03 | 2020-11-10 | 100%
|  | GUI Features | Midhuna Manchi | 2020-11-03 | 2020-11-10 | 100%
|  | Entitlements | Midhuna Manchi | 2020-11-03 | 2020-11-10 | 100%
|  | Data-Dependency Validation | Midhuna Manchi | 2020-11-03 | 2020-11-10 | 100%
|  | Connectivity | Midhuna Manchi | 2020-11-03 | 2020-11-10 | 100%
|  | Data Flow Out | Midhuna Manchi | 2020-11-03 | 2020-11-10 | 100%
| 03.03 Remove/add products to box | Core Functionality | Midhuna Manchi | 2020-11-03 | 2020-11-10 | 100%
|  | GUI Features | Midhuna Manchi | 2020-11-03 | 2020-11-10 | 100%
|  | Entitlements | Midhuna Manchi | 2020-11-03 | 2020-11-10 | 100%
|  | Data-Dependency Validation | Midhuna Manchi | 2020-11-03 | 2020-11-10 | 100%
|  | Calculations | Midhuna Manchi | 2020-11-03 | 2020-11-10 | 100%
|  | Connectivity | Midhuna Manchi | 2020-11-03 | 2020-11-10 | 100%
|  | Data Flow In | Midhuna Manchi | 2020-11-03 | 2020-11-10 | 100%
|  | Data Flow Out | Midhuna Manchi | 2020-11-03 | 2020-11-10 | 100%
MILESTONE 4: CODING COMPLETED
Integration & Testing | Update Project Plan with additional requirement tasks |  | Irina Sachovska | 2020-11-03 | 2020-11-10 | 100%
| Produce Test Plan document |  | Akshay Pesari | 2020-11-03 | 2020-11-10 | 100%
| Design Test Cases |  | Akshay Pesari | 2020-11-03 | 2020-11-10 | 100%
| Evaluate Features to be Tested: |  | Team | 2020-11-03 | 2020-11-10 | 100%
| 01.01 Login | Core Functionality | Midhuna Manchi | 2020-11-03 | 2020-11-10 | 100%
|  | GUI Features | Midhuna Manchi | 2020-11-03 | 2020-11-10 | 100%
|  | Data-Dependency Validation | Midhuna Manchi | 2020-11-03 | 2020-11-10 | 100%
|  | Connectivity | Midhuna Manchi | 2020-11-03 | 2020-11-10 | 100%
|  | Data Flow Out | Midhuna Manchi | 2020-11-03 | 2020-11-10 | 100%
|  | Exception Handling | Midhuna Manchi | 2020-11-03 | 2020-11-10 | 100%
| 01.02 SignUp | Core Functionality | Midhuna Manchi | 2020-11-03 | 2020-11-10 | 100%
|  | GUI Features | Midhuna Manchi | 2020-11-03 | 2020-11-10 | 100%
|  | Connectivity | Midhuna Manchi | 2020-11-03 | 2020-11-10 | 100%
|  | Data Flow Out | Midhuna Manchi | 2020-11-03 | 2020-11-10 | 100%
| 01.03 Restore Credentials | Core Functionality | Midhuna Manchi | 2020-11-03 | 2020-11-10 | 100%
|  | GUI Features | Midhuna Manchi | 2020-11-03 | 2020-11-10 | 100%
|  | Entitlements | Midhuna Manchi | 2020-11-03 | 2020-11-10 | 100%
|  | Field Validation | Midhuna Manchi | 2020-11-03 | 2020-11-10 | 100%
|  | Connectivity | Midhuna Manchi | 2020-11-03 | 2020-11-10 | 100%
|  | Data Flow Out | Midhuna Manchi | 2020-11-03 | 2020-11-10 | 100%
| 03.01 Select/Pause Plan | Core Functionality(Select/Pause) | Midhuna Manchi | 2020-11-03 | 2020-11-10 | 100%
|  | GUI Features | Midhuna Manchi | 2020-11-03 | 2020-11-10 | 100%
|  | Entitlements | Midhuna Manchi | 2020-11-03 | 2020-11-10 | 100%
|  | Data-Dependency Validation | Midhuna Manchi | 2020-11-03 | 2020-11-10 | 100%
|  | Connectivity | Midhuna Manchi | 2020-11-03 | 2020-11-10 | 100%
|  | Data Flow Out | Midhuna Manchi | 2020-11-03 | 2020-11-10 | 100%
| 03.03 Remove/add products to box | Core Functionality | Midhuna Manchi | 2020-11-03 | 2020-11-10 | 100%
|  | GUI Features | Midhuna Manchi | 2020-11-03 | 2020-11-10 | 100%
|  | Entitlements | Midhuna Manchi | 2020-11-03 | 2020-11-10 | 100%
|  | Data-Dependency Validation | Midhuna Manchi | 2020-11-03 | 2020-11-10 | 100%
|  | Calculations | Midhuna Manchi | 2020-11-03 | 2020-11-10 | 100%
|  | Connectivity | Midhuna Manchi | 2020-11-03 | 2020-11-10 | 100%
|  | Data Flow In | Midhuna Manchi | 2020-11-03 | 2020-11-10 | 100%
|  | Data Flow Out | Midhuna Manchi | 2020-11-03 | 2020-11-10 | 100%
| Execute Test Cases |  | Akshay Pesari | 2020-11-03 | 2020-11-10 | 100%
| Anaylze Test Results |  | Akshay Pesari | 2020-11-03 | 2020-11-10 | 100%
MILESTONE 5: TESTING COMPLETED
Project Presentation | Prepare Application Demo for the Presentation |  | Team | 2020-10-27 | 2020-11-24 | 100%